## Sheet1
Scenario No. | Module name | Scenario Description | Requirement ID | No. of conditions | Condition Description | Action No. | Action | Priority | Expected Result | Actual Result in Test Iteration 1 | Date | Status | Expected Result | Actual Result in Test Iteration 2 | Date | Status | Remarks
1 | NodeJS | Search by All | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 0 | Check by count | 1 |  | Low | Count of documents in dataset is 6019 | AssertionError: expected 6019 equal to 3667 | 2018-07-07 | Fail | Count of documents in dataset is 6019 | Count of documents in dataset is 6019 | 2018-07-07 | Pass
2 | NodeJS | Search by All | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 0 | Check by value | 2 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Hanover' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
3 | NodeJS | Search by All | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 0 | Check by datatype | 3 |  | Low | Data type of the field is 'string' | AssertionError: expected 'string' equal to 'number' | 2018-07-07 | Fail | Data type of the field is 'string' | Data type of the field is 'string' | 2018-07-07 | Pass
4 | NodeJS | Search by All | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 0 | Check by projection length | 4 |  | Low | Length of field projections in the document is 7 | AssertionError: expected 7 equal to 8 | 2018-07-07 | Fail | Length of field projections in the document is 7 | Length of field projections in the document is 7 | 2018-07-07 | Pass
5 | NodeJS | Search by All | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 0 | Check value using sort by Price | 5 |  | Low | Value of field in the document is 'Stockbridge' | AssertionError: expected 'Stockbridge' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Stockbridge' | Value of field in the document is 'Stockbridge' | 2018-07-07 | Pass
6 | NodeJS | Search by All | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 0 | Check value using sort by Year | 6 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
7 | NodeJS | Search by County | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check by count | 7 |  | Low | Count of documents in dataset is 2076 | AssertionError: expected 2076 equal to 1343 | 2018-07-07 | Fail | Count of documents in dataset is 2076 | Count of documents in dataset is 2076 | 2018-07-07 | Pass
8 | NodeJS | Search by County | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check by value | 8 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Lebanon' | 2018-07-06 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-06 | Pass
9 | NodeJS | Search by County | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check by datatype | 9 |  | Low | Data type of the field is 'string' | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | Data type of the field is 'string' | Data type of the field is 'string' | 2018-07-06 | Pass
10 | NodeJS | Search by County | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check value using sort by Price | 10 |  | Low | Value of field in the document is 'Enfield' | AssertionError: expected 'Enfield' equal to 'Canaan' | 2018-07-07 | Fail | Value of field in the document is 'Enfield' | Value of field in the document is 'Enfield' | 2018-07-07 | Pass
11 | NodeJS | Search by County | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check value using sort by Year | 11 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
12 | NodeJS | Seach by City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check by count | 12 |  | Low | Count of documents in dataset is 190 | AssertionError: expected 190 equal to 500 | 2018-07-06 | Fail | Count of documents in dataset is 190 | Count of documents in dataset is 190 | 2018-07-06 | Pass
13 | NodeJS | Seach by City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check by value | 13 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-06 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-06 | Pass
14 | NodeJS | Seach by City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check by datatype | 14 |  | Low | Data type of the field is 'string' | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | Data type of the field is 'string' | Data type of the field is 'string' | 2018-07-06 | Pass
15 | NodeJS | Seach by City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check value using sort by Price | 15 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Lebanon' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
16 | NodeJS | Seach by City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check value using sort by Year | 16 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
17 | NodeJS | Search by Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check by count | 17 |  | Low | Count of documents in dataset is 1031 | AssertionError: expected 1031 equal to 200 | 2018-07-06 | Fail | Count of documents in dataset is 1031 | Count of documents in dataset is 1031 | 2018-07-06 | Pass
18 | NodeJS | Search by Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check by value | 18 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-06 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-06 | Pass
19 | NodeJS | Search by Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check by datatype | 19 |  | Low | Data type of the field is 'string' | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | Data type of the field is 'string' | Data type of the field is 'string' | 2018-07-06 | Pass
20 | NodeJS | Search by Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check value using sort by Price | 20 |  | Low | Value of field in the document is 'Hartford' | AssertionError: expected 'Hartford' equal to 'Lebanon' | 2018-07-07 | Fail | Value of field in the document is 'Hartford' | Value of field in the document is 'Hartford' | 2018-07-07 | Pass
21 | NodeJS | Search by Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 1 | Check value using sort by Year | 21 |  | Low | Value of field in the document is 'Lebanon' | AssertionError: expected 'Lebanon' equal to 'Canaan' | 2018-07-07 | Fail | Value of field in the document is 'Lebanon' | Value of field in the document is 'Lebanon' | 2018-07-07 | Pass
22 | NodeJS | Search by County and City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check by count | 22 |  | Low | Count of documents in dataset is 190 | AssertionError: expected 190 equal to 250 | 2018-07-06 | Fail | Count of documents in dataset is 190 | Count of documents in dataset is 190 | 2018-07-06 | Pass
23 | NodeJS | Search by County and City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check by value | 23 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-06 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-06 | Pass
24 | NodeJS | Search by County and City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check by datatype | 24 |  | Low | Data type of the field is 'string' | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | Data type of the field is 'string' | Data type of the field is 'string' | 2018-07-06 | Pass
25 | NodeJS | Search by County and City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check value using sort by Price | 25 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
26 | NodeJS | Search by County and City | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check value using sort by Year | 26 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
27 | NodeJS | Search by County and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check by count | 27 |  | Low | Count of documents in dataset is 15 | AssertionError: expected 15 equal to 20 | 2018-07-06 | Fail | Count of documents in dataset is 15 | Count of documents in dataset is 15 | 2018-07-06 | Pass
28 | NodeJS | Search by County and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check by value | 28 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Lebanon' | 2018-07-06 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-06 | Pass
29 | NodeJS | Search by County and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check by datatype | 29 |  | Low | Data type of the field is 'string' | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | Data type of the field is 'string' | Data type of the field is 'string' | 2018-07-06 | Pass
30 | NodeJS | Search by County and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check value using sort by Price | 30 |  | Low | Value of field in the document is 'Lebanon' | AssertionError: expected 'Lebanon' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Lebanon' | Value of field in the document is 'Lebanon' | 2018-07-07 | Pass
31 | NodeJS | Search by County and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check value using sort by Year | 31 |  | Low | Value of field in the document is 'Lebanon' | AssertionError: expected 'Lebanon' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Lebanon' | Value of field in the document is 'Lebanon' | 2018-07-07 | Pass
32 | NodeJS | Search by City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check by count | 32 |  | Low | Count of documents in dataset is 1 | AssertionError: expected 1 equal to 10 | 2018-07-06 | Fail | Count of documents in dataset is 1 | Count of documents in dataset is 1 | 2018-07-06 | Pass
33 | NodeJS | Search by City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check by value | 33 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Lebanon' | 2018-07-06 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-06 | Pass
34 | NodeJS | Search by City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check by datatype | 34 |  | Low | Data type of the field is 'string' | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | Data type of the field is 'string' | Data type of the field is 'string' | 2018-07-06 | Pass
35 | NodeJS | Search by City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check value using sort by Price | 35 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
36 | NodeJS | Search by City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 2 | Check value using sort by Year | 36 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
37 | NodeJS | Search by County,City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 3 | Check by count | 37 |  | Low | Count of documents in dataset is 1 | AssertionError: expected 1 equal to 15 | 2018-07-06 | Fail | Count of documents in dataset is 1 | Count of documents in dataset is 1 | 2018-07-06 | Pass
38 | NodeJS | Search by County,City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 3 | Check by value | 38 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-06 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-06 | Pass
39 | NodeJS | Search by County,City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 3 | Check by datatype | 39 |  | Low | Data type of the field is 'string' | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | Data type of the field is 'string' | Data type of the field is 'string' | 2018-07-06 | Pass
40 | NodeJS | Search by County,City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 3 | Check value using sort by Price | 40 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfeld' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass
41 | NodeJS | Search by County,City and Price | Scrum-4 Testing,-> Sprint 2 (1D) -> User Story 1 | 3 | Check value using sort by Year | 41 |  | Low | Value of field in the document is 'Canaan' | AssertionError: expected 'Canaan' equal to 'Enfield' | 2018-07-07 | Fail | Value of field in the document is 'Canaan' | Value of field in the document is 'Canaan' | 2018-07-07 | Pass